## Sheet1
Task ID | Task Name | Owner | Planned Start | Planned End | Status
TASK001 | Requirements Gathering | Anita | 2025-04-01 | 2025-04-04 | Completed
TASK002 | Vendor Finalization | Rohit | 2025-04-05 | 2025-04-09 | Completed
TASK003 | Procurement | Vikas | 2025-04-10 | 2025-04-14 | In Progress
TASK004 | Site Setup | Sonal | 2025-04-15 | 2025-04-19 | Not Started
TASK005 | UAT Planning | Meera | 2025-04-20 | 2025-04-25 | Not Started